## Sheet1
1 | Feature for ANDROID: USER FOCUS | Requirement | Prototype | Development | Integration | Deployment to Cloud
2 | WELCOME TO OUR APP! | Completed | Completed | Completed | Completed
3 | CRUD of user's profile (checkbox for user to check to indicate agreement) | Completed | Completed | Completed | Completed
4 | login & logout | Completed | Completed | Completed | Completed
5 | list out agreement (document) | Completed | Completed | Completed | Completed
6 | Forum landing page | Completed | Completed | Completed | Completed
7 | View a topic page | Completed | Completed | Completed | Completed
8 | Create a new topic | Completed | Completed | Completed | Completed
9 | Search bar for topics (Topic list page) Results of search | Completed | Completed | Completed | Completed
10 | messaging function (CRUD) + make sure that messaging ability only appear if both users are matched together | Cancelled (After discussion, the team has decided to complete the forum feature first and put the messaging feature to be developed in the next scrum. As doing both in one scrum is too heavy for the team)
11 | Individual chat
12 | Friends landing page | Completed | Completed | Completed | Completed
13 | Potential Matches rating of user (by their messages on forum) | Completed | Completed | Completed | Completed
14 | User Details page | Completed | Completed | Completed | Completed
15 | Manage Friends (CRUD) | Completed | Completed | Completed | Completed
16 | List of users with sorting and classification function | Completed | Completed | Completed | Completed
17 | users suspended (on 2nd warning 3 days, 3rd warning 2 week) | Completed | Completed | Completed | Completed
18 | User given first warning | Removed from this sprint |  |  | Renove from this sprint
19 | push notification when messages/forum comments comes in | Completed | Completed | Completed | Completed
20 | Connect to firebase from Android | Completed | Completed | Completed | Completed
21 | Feature for WEB: ADMIN
22 | Admin can login and logout of the admin dashboard | Completed | Completed | Completed | Completed
23 | Admin can view admin dashboard | Completed | Completed | Completed | Completed
24 | As an administrator, I want to be able to suspend users and/or send them a warning if they are found abusing the platform with misconduct, fake profiles and threatening or distasteful behavior. | Completed | Completed | Completed | Completed
25 | Admin can view signed user agreement on user detail page | Completed | Completed | Completed | Completed
26 | Connect to firebase from JavaWeb | Completed | Completed | Completed | Completed
27 | Admin can do sentimental analysis on user comments/topics | Completed | Completed | Completed | Completed